## Slide 1: Records Process Flow Improvement
Manual  Digital

## Slide 2: Records Process Flow Improvement Incoming Communications
Existing
1. Receive and time-stamp the document.
2. Encode document subject, sender name and address to DTS (Data Tracking System).
3. Print transmittal slip from DTS.
4. Write the DTS-generated reference number to the document.
5. Encode details to monitoring log sheet (subject, sender name and address, time received)
6. Scan document and save to OneDrive. Attach the printed transmittal slip.
7. Print the updated log sheet.
8. Endorse document to OPM.
9. PM writes instructions on the transmittal slip and physically routed/endorsed to concerned RC.
Proposed
1. Receive and time-stamp the document.
2. Scan document and upload to an Electronic Document Management System (EDMS). *Scanned document is converted to PDF and Optical Character Recognition (OCR)-enabled.
3. EDMS assigns control/tracking number and embeds it in the scanned document.
4. Details (subject, sender name and address) are copied from scanned document into the transmittal slip template of the EDMS. Details are automatically saved to a monitoring log sheet.
5. Print the transmittal slip and the generated control/tracking number is printed to a sticker. Attach transmittal slip and sticker to document.
6. Document/s are both physically and digitally (accessed thru EDMS) endorsed to OPM.
7. PM may route the document physically and/or digitally to concerned RC.

## Slide 3: Records Process Flow Improvement Outgoing Communications
Existing
1. Receive and time-stamp the document.
2. Encode/Log time received, sender details (RC and sender’s initials), document subject, recipient and CF party.
3. Write reference code/number on all copies.
4. Scan document and save to OneDrive. File Record’s hardcopy to storage.
5. Batch/Group documents (for HO, PMO, TMOs, other PMOs, external recipient/s).
6. Prepare transmittals for documents for PPA recipients.
7. Dispatch documents (via courier, PMO assigned driver, personally handed)
Proposed
1. Receive and time-stamp the document.
2. Scan document and upload to an Electronic Document Management System (EDMS). *Scanned document is converted to PDF and Optical Character Recognition (OCR)-enabled.
3. EDMS assigns reference code/number and embeds it in the scanned document.
4. Details (time received, sender details, document subject, recipient and CF party ) are extracted from the scanned document into the monitoring log sheet.
5. EDMS will classify logged documents according to recipient and generate transmittals (for HO, PMO, TMOs, other PMOs)
6. Print the generated reference code/number sticker. Attach sticker/s according to the number of copies per outgoing document.
7. Dispatch documents (via courier, PMO assigned driver, personally handed)

## Slide 4
Key System Interactions:
Document Reception: Physical document arrives; operator initiates process in system.
Timestamp: Automatic recording of date/time received.
Scanner Integration: Network scanner sends images directly to the system.
OCR Engine: Extracts text from scanned documents for auto-population.
Database: Stores all metadata, file paths, and routing history.
Excel Log: Real-time updates for monitoring purposes (optional, as database is primary).
Print Service: Generates transmittal slips and control number stickers.
Digital Routing: EDMS handles permissions and notifications for digital endorsement.
System Process Flow (Textual Diagram)

## Slide 5
Phase / Task | Duration | Start Week | End Week | Dependencies
Phase 1: Requirements & Planning | 4 weeks | 1 | 4 | –
1.1 Gather detailed requirements | 2 week | 1 | 2 | –
1.2 Define system architecture | 2 week | 3 | 4 | 1.1
1.3 Set up the building tools | 0.5 week | 4 | 4 | 1.2
PROJECT TIMELINE

## Slide 6
Phase 2: Design | 4 weeks | 4 | 8 | Phase 1
2.1 Setting up the document database structure | 2 week | 4 | 6 | 1.2
2.2 User Interface/UX mockups | 2 week | 6 | 8 | 2.1
2.3 Transmittal slip template design | 0.5 week | 8 | 8 | 2.1

## Slide 7
Phase 3: Development – Core Modules | 14 weeks | 9 | 23 | Phase 2
3.1 Sprint 1: Auth, Document Intake, Timestamp | 4 weeks | 9 | 13 | 2.2
3.2 Sprint 2: Upload, PDF Conversion, OCR | 4 weeks | 13 | 17 | 3.1
3.3 Sprint 3: Control # Assignment, PDF Stamping | 4 weeks | 17 | 21 | 3.2
3.4 Sprint 4: Data Extraction, Excel Log | 2 week | 21 | 23 | 3.3

## Slide 8
Phase 4: Development – Routing & Printing | 6 weeks | 23 | 29 | Phase 3
4.1 Sprint 5: Transmittal Slip Generation | 2 week | 23 | 25 | 3.4
4.2 Sprint 6: Sticker Printing, Print Queue | 2 week | 25 | 27 | 4.1
4.3 Sprint 7: Routing Workflow (OPM → RC) | 2 week | 27 | 29 | 4.2

## Slide 9
Phase 5: Testing & QA | 6 weeks | 29 | 35 | Phase 4
5.1 Unit & integration testing | 3 weeks | 29 | 32 | 4.3
5.2 User acceptance testing (UAT) | 2 week | 32 | 34 | 5.1
5.3 Bug fixing & refinement | 1 week | 34 | 35 | 5.2

## Slide 10
Phase 6: Deployment & Training | 4 weeks | 35 | 39 | Phase 5
6.1 Deploy to production | 1 week | 35 | 36 | 5.3
6.2 User training & documentation | 3 weeks | 36 | 39 | 6.1
Total estimated duration: 40 weeks (including buffer).

## Slide 11
Software Requirements
1. Development Framework & Programming Languages
Component | Recommended Options | Purpose
Backend Framework | Django (Python) or Flask (Python) | Main application framework to handle document processing, user authentication, and business logic
Programming Language | Python 3.9+ | Core language with extensive libraries for OCR, PDF manipulation, and Excel integration
Frontend | HTML, CSS, JavaScript, Bootstrap | User interface for staff to interact with the system

## Slide 12
2. Database
Component | Recommended Options | Purpose
Database System | PostgreSQL 13+ or MySQL | Store document metadata, tracking numbers, routing history, and user information
Database Tools | pgAdmin (for PostgreSQL) or phpMyAdmin (for MySQL) | Database administration and management

## Slide 13
3. OCR & Document Processing Libraries
Component | Recommended Options | Purpose
OCR Engine | Tesseract OCR (open-source) or EasyOCR or PaddleOCR | Convert scanned images to searchable/editable text
PDF Processing | PyPDF2, pdfplumber, or pdf2image | Manipulate PDFs, embed tracking numbers, convert images to PDF
Image Processing | OpenCV-Python, Pillow (PIL) | Process scanned images before OCR

## Slide 14
4. QR Code & Barcode Handling
Component | Recommended Options | Purpose
QR Code Generation | qrcode (Python library) | Generate QR codes for division tracking
QR Code Scanning | pyzbar, OpenCV | Read QR codes from scanner/camera input
Barcode Support | python-barcode | Generate control number barcodes if needed

## Slide 15
5. Excel & Reporting
Component | Recommended Options | Purpose
Excel Integration | pandas, openpyxl | Append document details to monitoring log sheet automatically
Report Generation | ReportLab, WeasyPrint | Generate printable transmittal slips and sticker sheets

## Slide 16
6. Web Server & Deployment
Component | Recommended Options | Purpose
Web Server | Nginx or Apache | Serve the application to users
WSGI Server | Gunicorn or uWSGI | Run Python application in production
Containerization | Docker (optional) | Simplify deployment and environment consistency

## Slide 17
7. Operating System
Component | Recommended Options | Purpose
Server OS | Windows Server 2019/2022 or Ubuntu Server 20.04 LTS+ | Host the application and database
Client OS | Windows 10/11 (for staff workstations) | Access the web-based system

## Slide 18
Hardware Requirements
1. Server Hardware
Storage Note: A 256 GB drive can hold approximately 50,000-100,000 scanned documents (depending on file size). Plan for growth .
Component | Minimum Recommendation | Recommended for Production | Notes
Processor (CPU) | 4 cores, 2.0 GHz+ | 8+ cores, 2.5 GHz+ | More cores for handling multiple document uploads simultaneously
Memory (RAM) | 8 GB | 16-32 GB | OCR and PDF processing are memory-intensive
Storage (Hard Drive) | 256 GB SSD | 512 GB+ SSD | SSD strongly recommended for database performance
Network | Gigabit Ethernet | Gigabit Ethernet | For fast document transfer

## Slide 19
2. Workstation/Client Computers
Component | Recommendation | Purpose
Processor | Intel Core i5 or equivalent | Run web browser and connect to scanner
Memory | 8 GB RAM | Smooth multitasking
Storage | 256 GB SSD | Local storage if needed
Display | 1080p monitor | View documents clearly
Operating System | Windows 10/11 Pro | Compatible with most scanners and printers

## Slide 20
3. Scanner
Scanner Integration Options:
Option A (Recommended): Scanner saves to a network folder; Python app monitors folder and auto-processes new files
Option B: Scanner with API integration (more complex but real-time)
Option C: USB scanner connected to workstation with manual upload trigger
Component | Recommendation | Why It Matters
Type | Network scanner with ADF (Automatic Document Feeder) | Scan multiple pages without manual feeding
Recommended Model | Plustek eScan A450 Pro or similar network scanner | Scans directly to network folder; built-in OCR; 7" touchscreen; scans to PDF; 60 ppm speed
Key Features Needed | - Duplex scanning (both sides) - 600 dpi optical resolution - Scan to network folder (SMB/FTP) - 50+ sheet ADF capacity - Daily duty cycle: 8,000+ pages | Matches workflow requirements
Alternative | Fujitsu fi series or Canon imageFORMULA | Reliable workgroup scanners

## Slide 21
4. QR Code Scanner
Component | Recommendation | Purpose
Type | USB 2D barcode/QR scanner | Plug-and-play with workstation
Recommended Features | - Reads 2D QR codes and 1D barcodes - Hands-free operation (stand included) - USB connection - Reads OCR fonts (optional) | 
Examples | Honeywell Granit, Zebra DS2208, Opticon MDI-4700 series | Reliable brands with good support
Alternative | Webcam + QR software | Lower cost but less reliable for high volume

## Slide 22
5. Printers
Component | Recommendation | Purpose
Label Printer | Zebra GK420d or Brother QL-800 | Print control number stickers
Label Type | Direct thermal labels (no ink/toner needed) | Cost-effective for stickers
Transmittal Slip Printer | Standard office laser printer (e.g., HP LaserJet) | Print transmittal slips on plain paper

## Slide 23
6. Networking Equipment
Component | Recommendation | Purpose
Network Switch | Gigabit Ethernet switch (8+ ports) | Connect server, workstations, scanner, printers
Wi-Fi | Optional—wired recommended for reliability | Wireless for staff convenience if needed
Cabling | Cat5e or Cat6 Ethernet cables | Stable network connections

## Slide 24
Expand details on the system/electronic transmission of the document from Records to OPM to concerned Divisions.
List add-ons or future improvements (such as notification for concerned RC, etc.)